## Sheet1
Requirements | Sprint | Topic | User Story | Task # | Task | Priority | Assigned To | Start Date | End Date | Hours[Task Based] Estimate the testing+development-Technical Panel | StoryPoint[Businessvalue/complexity] Estimates how much we can deliver in a spring+total effort with its tasks with its depencies and other factors[Po+scrum] | Status
| #1 | Customer Registration | As a customer, I want to open customer registration page and save the entered customer details. | Task#1 | Project setup and configuration and access to Login/Registration Page | High | Abhishek | 2019-11-03 | 2019-12-03 | 1 |  | Done
|  |  |  | Task#2 | Create Login JSP page | High | Rajan | 2019-11-03 | 2019-11-03 | 1 |  | Done
|  |  |  | Task#3 | Field Validations on Login JSP | Medium | Rajan | 2019-12-03 | 2019-12-03 | 2 |  | Done
|  |  |  | Task#4 | Create a Registration JSP page to accept the data from User as per the field of User table. | High | Rajan | 13/3/19 | 13/3/19 | 2 |  | Done
|  |  |  | Task#5 | Create User class, User DAO and User Service class to insert the user data and controller and verify on backend. | High | Abhishek | 13/3/19 | 13/3/19 | 1 |  | Done
|  |  |  | Task#6 | Integrate the code and verify its working . | High | Abhishek | 14/3/19 | 14/3/19 | 1 |  | Done
| #2 | Tour Search | As a customer, I want to search tour between particular cities | Task#7 | Create a JSP page to accept date, source, destination and number of travellers from user (Home Page after login) | High | Rajan | 14/3/19 | 14/3/19 | 2 |  | Done
|  |  |  | Task#8 | Manually create source_destination table in holiday_planner database and insert records for source and destination cities | High | Saksham | 14/3/19 | 14/3/19 | 1 |  | Done
|  |  |  | Task#9 | Create Tour class, Tour DAO and Tour Service class to search the tour data and controller and verify on backend. | High | Abhishek | 15/3/19 | 15/3/19 | 1 |  | Done
|  |  |  | Task#10 | Fields Validations on Book Tour Form at Home JSP | Medium | Rajan | 18/3/19 | 18/3/19 | 2 |  | Done
| #3 | Generate Bill | As a customer, I want to see the final amount with bill for a particular tour. | Task#11 | Create a GenerateBill JSP page to show the bill as per the tour details. | High | Rajan | 19/3/19 | 19/3/19 | 2 |  | Done
|  |  |  | Task#12 | Create Bill Bean and GenerateBill method in Tour DAO and Tour Service and controller to get bill details | High | Abhishek | 18/3/19 | 19/3/19 | 1 |  | Done
|  |  |  | Task#13 | After generating bill set payment_status to pending in database | High | Abhishek | 19/3/19 | 19/3/19 | 1 |  | Done
|  |  |  | Task#14 | Integrate the code and verify its working. | High | Abhishek | 20/3/19 | 20/3/19 | 1 |  | Done
|  |  |  | Task#15 | Provide an option to download the generated bill | High | Saksham | 20/3/19 | 20/3/19 | 2 |  | Done
| #4 | Bill Payment | As a customer, I want to pay for the bill to book tour. | Task#16 | Create Payment JSP page which shows various payment options. | High | Rajan | 21/3/19 | 21/3/19 | 2 |  | Done
|  |  |  | Task#17 | Redirect to payment and provide payment options to the user. | High | Abhishek | 21/3/19 | 21/3/19 | 1 |  | Done
|  |  |  | Task#18 | Create JSPs for various Payment options like Debit/Credit Card, Net Banking and UPI. | High | Rajan | 22/3/19 | 22/3/19 | 2 |  | Done
|  |  |  | Task#19 | Create JSP to get debit/credit card details from user. | High | Rajan | 22/3/19 | 22/3/19 | 2 |  | Done
|  |  |  | Task#20 | Create a JSP to show payment success or failure. | High | Rajan | 25/3/19 | 25/3/19 | 2 |  | Done
|  |  |  | Task#21 | After successful payment redirect to paymentSuccess page and generate receipt and set payment_status to paid in the database. | High | Abhishek | 25/3/19 | 25/3/19 | 1 |  | Done
|  |  |  | Task#22 | Provide an option to download the receipt. | Medium | Saksham | 25/3/19 | 25/3/19 | 1 |  | Done
| #5 | Logout and Basic Testing | Logout Option and check flow of the process. | Task#23 | Provide a logout option at every page. | High | Rajan | 26/3/19 | 26/3/19 | 2 |  | Done
|  |  |  | Task#24 | Perform basic testing and check flow of the tour booking process. | Medium | Saksham | 26/3/19 | 26/3/19 | 3 |  | Done